## IMP_&_RB_Plan
RBL Bank
Activity: | MyCard Middleware Deployment
Prepared Date: | 2024-09-02
Prepared By: | Karan Choudhari
Change No. | 19041
Activity Date: | TBD
Implementation Plan
Sr No | Plan of Action | Activity Owner | Time in Minute | Date & Time Slot | Risk & Impact Analysis | Services Impact | Remarks From Implementation Team | Status
1 | Winjit Team to check in the latest Deployable in RBL GIT Mycard-Middleware-dl | Winjit |  | Before the deployment
2 | IT release team or Nagul/Chandra to trigger the jenkins job for Autodeployment | IT Release team or Nagul/ Chandra | 2 | at the time of deployment |  | Yes 2 Mins of downtime for one server.
|  | Total time in Minutes | 2
Rollback Plan
Sr No | Plan of Action | Activity Owner | Time in Minute | Date and Time Slot | Risk & Impact Analysis | Services Impact | Remarks From Implementation Team | Status
1 | Winjit Team to check in the latest deployable in RBL GIT Mycard-Middleware-dl | Winjit |  | at rollback instance
2 | IT release team or Nagul/Chandra to trigger the jenkins job for Autodeployment | IT Release team or Nagul/ Chandra | 2 | at rollback instance | Services Are Down in case and Up within second after rollback is done.
|  | Total time in Minutes | 2

## Release Note
Application/DB Name | MyCard | Release Type | Business Requirement | Change Number | 19041 | Requester Name/Team | Winjit | Environment | Production
Server/ Device/ DB IP |  | 10.80.65.65 & 10.80.65.66
Implementation Plan | A. Deploy Middleware:(On both servers one by one) AutoDeployment 1. Winjit Team to check in the latest deployable in RBL GIT Mycard-Middleware-dl.(deployable as rhel-x64 File) 2. IT Release manager to trigger the jenkins job for deployment of MyCard Middleware from Main branch as per git checkin |  |  |  | Roll Back Plan | Rollback Steps (AutoDeployment ) Check in the existing working Configs into GIT Mycard-Middleware-dl and IT release manager to trigger the Jenkins job for deployment
Git Link
BugFix
Enhancement
Datapatch
Compliance/ Regulatory
Business Requirement
BAU
Others